## Settings
Field | Value
Dashboard Title | Anshul's Weekly Update
Manager | Rohan Banaik
Last Updated | 2026-09-15

## DL RFP
Activity | Target Date | Actual Completion Date | Status | Remarks
RFP Issue | Aug 19th | Aug 19th | Completed
Supplier to Submit Clarification Questions | Aug 26th | Aug 26th | Completed
GSK to respond to Clarification Questions | Aug 28th | Aug 28th | Completed
Supplier to Submit Proposal | Sept 2nd | Sept 2nd | Completed
Supplier Presentations | Sept 3rd- 11th | Sept 3rd- 11th | Completed
Award | Sept 25th |  | In-Progress
POC | Nov 1st
Stakeholder
John Smith
Sarah Williams
David Brown
Jane Doe
Committed Spend
£550,000
REMARKS
Commercial evaluation is currently underway.

## Exhibition Services RFP
Activity | Target Date | Actual Completion Date | Status | Remarks
Supplier Landscape deck | September 8th | September 8th | Completed
Stakeholder
Peter allen
Committed Spend
Na
REMARKS
Na

## SuSo
Activity | Target Date | Actual Completion Date | Status | Remarks
Identify full directs spend from Global Invoice Viewer (July 2025 – July 2026 period) | 1 week | 1st Sept | Completed
Identify purchases that can be excluded based on materiality thresholds | 1 week | 8th Sept | Completed
Identification of naturally derived materials with material and category codes | 1 week | 15th Sept | Completed
Stakeholder
Sophiee blackburn
Helen Mcfaden
Thomas newbigging
Committed Spend
Na
REMARKS
Na